## WBS
Portfolio Project — WBS (AI Support Ticket System) - 7-Week
Project start date (Monday): |  | 2026-10-07
Legend: edit only the yellow start date and the Status column (yellow). Blue numbers = estimated hours (6.5 h/day, split evenly). Everything else is formulas.
WBS ID | Level | Work item | Type | Week | Day | Start | Finish | Est. hours | Status | % complete | Earned hours | Notes | Watch (YouTube search) | Read (docs / article)
1 | 1 | AI Support Ticket System portfolio project | Project |  |  | 2026-10-07 | 2026-11-24 | 227.7 |  | 15.7% | 35.74
1.1 | 2 | Week 1: Foundations | Phase | 1 |  | 2026-10-07 | 2026-10-07 | 32.49 |  | 100% | 32.49
1.1.1 | 3 | Day 1: Environment | Work package | 1 | 1 | 2026-10-07 | 2026-10-07 | 6.48 | Done | 100% | 6.48
1.1.1.1 | 4 | Read what changed in the latest Laravel release | Task | 1 | 1 | 2026-10-07 | 2026-10-07 | 1.62 | Done | 100% | 1.62 |  | YouTube: Laravel 13 new features | Laravel docs: Release notes
1.1.1.2 | 4 | Create public GitHub repo; Docker Compose with PHP, PostgreSQL (pgvector), Redis | Task | 1 | 1 | 2026-10-07 | 2026-10-07 | 1.62 | Done | 100% | 1.62 |  | YouTube: docker compose laravel postgres redis | Docker docs: Compose
1.1.1.3 | 4 | Install Laravel; confirm app, database and Redis connect | Task | 1 | 1 | 2026-10-07 | 2026-10-07 | 1.62 | Done | 100% | 1.62 |  | YouTube: laravel docker setup postgresql | Laravel docs: Installation
1.1.1.4 | 4 | First commit + DEVLOG.md | Task | 1 | 1 | 2026-10-07 | 2026-10-07 | 1.62 | Done | 100% | 1.62 |  | YouTube: git basics tutorial | Pro Git book
1.1.2 | 3 | Day 2: Domain design | Work package | 1 | 2 | 2026-10-08 | 2026-10-08 | 6.51 | Done | 100% | 6.51
1.1.2.1 | 4 | Draw ERD: organizations, users, roles, tickets, messages, categories, SLA policies, KB articles | Task | 1 | 2 | 2026-10-08 | 2026-10-08 | 2.17 | Done | 100% | 2.17 |  | YouTube: database design entity relationship diagram | Mermaid: ER diagrams
1.1.2.2 | 4 | Write ADR-001: multi-tenancy approach | Task | 1 | 2 | 2026-10-08 | 2026-10-08 | 2.17 | Done | 100% | 2.17 |  | YouTube: multi tenancy single database vs database per tenant | Azure: Tenancy models
1.1.2.3 | 4 | Migrations, models, relationships, factories | Task | 1 | 2 | 2026-10-08 | 2026-10-08 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel eloquent relationships factories | Laravel docs: Relationships
1.1.3 | 3 | Day 3: Auth and roles | Work package | 1 | 3 | 2026-10-09 | 2026-10-09 | 6.51 | Done | 100% | 6.51
1.1.3.1 | 4 | Install Laravel React starter kit (Inertia + TypeScript) for auth | Task | 1 | 3 | 2026-10-09 | 2026-10-09 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel react starter kit inertia | Laravel docs: Starter kits
1.1.3.2 | 4 | Roles (admin, agent, customer) and ticket policies | Task | 1 | 3 | 2026-10-09 | 2026-10-09 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel policies gates authorization | Laravel docs: Authorization
1.1.3.3 | 4 | Tenant middleware: scope every request to the user's organization | Task | 1 | 3 | 2026-10-09 | 2026-10-09 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel multi tenancy global scope subdomain | Laravel docs: Global scopes
1.1.4 | 3 | Day 4: Pest | Work package | 1 | 4 | 2026-10-12 | 2026-10-12 | 6.51 | Done | 100% | 6.51
1.1.4.1 | 4 | Learn Pest basics: it(), expect(), datasets, RefreshDatabase | Task | 1 | 4 | 2026-10-12 | 2026-10-12 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel testing tutorial | Laravel docs: Testing
1.1.4.2 | 4 | Tests: tenant isolation | Task | 1 | 4 | 2026-10-12 | 2026-10-12 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel multi tenancy testing data isolation | Laravel docs: Database testing
1.1.4.3 | 4 | Tests: role permissions | Task | 1 | 4 | 2026-10-12 | 2026-10-12 | 2.17 | Done | 100% | 2.17 |  | YouTube: laravel testing authorization policies | Laravel docs: HTTP tests
1.1.5 | 3 | Day 5: Code quality + review | Work package | 1 | 5 | 2026-10-13 | 2026-10-13 | 6.48 | Done | 100% | 6.48
1.1.5.1 | 4 | Add Pint and Larastan; fix findings | Task | 1 | 5 | 2026-10-13 | 2026-10-13 | 1.62 | Done | 100% | 1.62 |  | YouTube: larastan phpstan laravel | Larastan on GitHub
1.1.5.2 | 4 | Move ticket logic into action classes | Task | 1 | 5 | 2026-10-13 | 2026-10-13 | 1.62 | Done | 100% | 1.62 |  | YouTube: laravel action classes pattern | Search: laravel action classes pattern
1.1.5.3 | 4 | Seeders: 2 organizations, users per role, sample tickets | Task | 1 | 5 | 2026-10-13 | 2026-10-13 | 1.62 | Done | 100% | 1.62 |  | YouTube: laravel seeders factories | Laravel docs: Seeding
1.1.5.4 | 4 | Week review: tests green, README stub | Task | 1 | 5 | 2026-10-13 | 2026-10-13 | 1.62 | Done | 100% | 1.62 |  | YouTube: how to write a good README github | Make a README
1.2 | 2 | Week 2: Frontend | Phase | 2 |  | 2026-10-14 | 2026-10-20 | 32.53 |  | 9.991% | 3.25
1.2.1 | 3 | Day 6: TypeScript | Work package | 2 | 6 | 2026-10-14 | 2026-10-14 | 6.5 | In progress | 50% | 3.25
1.2.1.1 | 4 | Learn types, interfaces, unions, generics, typing React props/events | Task | 2 | 6 | 2026-10-14 | 2026-10-14 | 3.25 | Not started | 0% | 0 |  | YouTube: typescript tutorial for beginners | TypeScript Handbook
1.2.1.2 | 4 | Shared types for Ticket, Message, User | Task | 2 | 6 | 2026-10-14 | 2026-10-14 | 3.25 | Done | 100% | 3.25 |  | YouTube: typescript react props types | React docs: Using TypeScript
1.2.2 | 3 | Day 7: Inertia + ticket list | Work package | 2 | 7 | 2026-10-15 | 2026-10-15 | 6.5 | Not started | 0% | 0
1.2.2.1 | 4 | Learn Inertia: pages, props, layouts, shared data, useForm | Task | 2 | 7 | 2026-10-15 | 2026-10-15 | 3.25 | Not started | 0% | 0 |  | YouTube: inertia.js laravel react tutorial | Inertia docs: Pages
1.2.2.2 | 4 | Ticket list page: pagination, filters, search | Task | 2 | 7 | 2026-10-15 | 2026-10-15 | 3.25 | Done | 0% | 0 |  | YouTube: laravel inertia pagination filters search | Laravel docs: Pagination
1.2.3 | 3 | Day 8: Create + detail | Work package | 2 | 8 | 2026-10-16 | 2026-10-16 | 6.51 | Not started | 0% | 0
1.2.3.1 | 4 | Create ticket form with validation errors | Task | 2 | 8 | 2026-10-16 | 2026-10-16 | 2.17 | Done | 0% | 0 |  | YouTube: inertia useForm validation errors react | Inertia docs: Forms
1.2.3.2 | 4 | Ticket detail page with message thread and replies | Task | 2 | 8 | 2026-10-16 | 2026-10-16 | 2.17 | Done | 0% | 0 |  | YouTube: laravel inertia react crud | Laravel docs: Eager loading
1.2.3.3 | 4 | File attachments (local storage) | Task | 2 | 8 | 2026-10-16 | 2026-10-16 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel file upload inertia react | Laravel docs: File storage
1.2.4 | 3 | Day 9: Agent view | Work package | 2 | 9 | 2026-10-19 | 2026-10-19 | 6.51 | Not started | 0% | 0
1.2.4.1 | 4 | Assign, change status/priority, internal notes | Task | 2 | 9 | 2026-10-19 | 2026-10-19 | 2.17 | Done | 0% | 0 |  | YouTube: laravel validation rules tutorial | Laravel docs: Validation
1.2.4.2 | 4 | Flash messages; empty and loading states | Task | 2 | 9 | 2026-10-19 | 2026-10-19 | 2.17 | Not started | 0% | 0 |  | YouTube: inertia flash messages laravel | Inertia docs: Shared data
1.2.4.3 | 4 | Feature tests for each action | Task | 2 | 9 | 2026-10-19 | 2026-10-19 | 2.17 | Done | 0% | 0 |  | YouTube: laravel feature tests | Laravel docs: HTTP tests
1.2.5 | 3 | Day 10: CI | Work package | 2 | 10 | 2026-10-20 | 2026-10-20 | 6.51 | Not started | 0% | 0
1.2.5.1 | 4 | GitHub Actions: Pint, Larastan, Pest, type-check, frontend build | Task | 2 | 10 | 2026-10-20 | 2026-10-20 | 2.17 | Done | 0% | 0 |  | YouTube: github actions laravel ci | GitHub Actions docs
1.2.5.2 | 4 | CI badge in README; fix anything red | Task | 2 | 10 | 2026-10-20 | 2026-10-20 | 2.17 | Done | 0% | 0 |  | YouTube: github actions status badge readme | Search: github actions workflow status badge
1.2.5.3 | 4 | Week review | Task | 2 | 10 | 2026-10-20 | 2026-10-20 | 2.17 | Not started | 0% | 0
1.3 | 2 | Week 3: Business logic | Phase | 3 |  | 2026-10-21 | 2026-10-27 | 32.54 |  | 0% | 0
1.3.1 | 3 | Day 11: SLA policies + events | Work package | 3 | 11 | 2026-10-21 | 2026-10-21 | 6.51 | Not started | 0% | 0
1.3.1.1 | 4 | SLA policy per priority: first-response and resolution deadlines | Task | 3 | 11 | 2026-10-21 | 2026-10-21 | 2.17 | Done | 0% | 0 |  | YouTube: what is SLA first response time customer support | Wikipedia: Service-level agreement
1.3.1.2 | 4 | Events: TicketCreated, TicketReplied, TicketStatusChanged | Task | 3 | 11 | 2026-10-21 | 2026-10-21 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel events listeners | Laravel docs: Events
1.3.1.3 | 4 | Calculate and store due dates on ticket creation | Task | 3 | 11 | 2026-10-21 | 2026-10-21 | 2.17 | Done | 0% | 0 |  | YouTube: laravel carbon dates tutorial | Carbon docs
1.3.2 | 3 | Day 12: Queues + Horizon | Work package | 3 | 12 | 2026-10-22 | 2026-10-22 | 6.51 | Not started | 0% | 0
1.3.2.1 | 4 | Learn Redis queues and Horizon; queue worker in Docker | Task | 3 | 12 | 2026-10-22 | 2026-10-22 | 2.17 | In progress | 0% | 0 |  | YouTube: laravel horizon redis queues | Laravel docs: Horizon
1.3.2.2 | 4 | Queued listeners for the events | Task | 3 | 12 | 2026-10-22 | 2026-10-22 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel queued event listeners | Laravel docs: Queued listeners
1.3.2.3 | 4 | Scheduled command: find SLA breaches, dispatch escalation job | Task | 3 | 12 | 2026-10-22 | 2026-10-22 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel task scheduling | Laravel docs: Task scheduling
1.3.3 | 3 | Day 13: Notifications | Work package | 3 | 13 | 2026-10-23 | 2026-10-23 | 6.5 | Not started | 0% | 0
1.3.3.1 | 4 | Mail (Mailpit) + database notifications for assign, reply, breach | Task | 3 | 13 | 2026-10-23 | 2026-10-23 | 3.25 | In progress | 0% | 0 |  | YouTube: laravel notifications mail database | Laravel docs: Notifications
1.3.3.2 | 4 | Notification bell in the UI | Task | 3 | 13 | 2026-10-23 | 2026-10-23 | 3.25 | Not started | 0% | 0 |  | YouTube: laravel notification bell inertia react | Laravel docs: Database notifications
1.3.4 | 3 | Day 14: Public REST API | Work package | 3 | 14 | 2026-10-26 | 2026-10-26 | 6.51 | Not started | 0% | 0
1.3.4.1 | 4 | Sanctum API tokens per organization | Task | 3 | 14 | 2026-10-26 | 2026-10-26 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel sanctum api tokens | Laravel docs: Sanctum
1.3.4.2 | 4 | Endpoints: create, list, show; API Resources; rate limiting | Task | 3 | 14 | 2026-10-26 | 2026-10-26 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel api resources rate limiting | Laravel docs: API resources
1.3.4.3 | 4 | Generate API docs (e.g. Scribe) | Task | 3 | 14 | 2026-10-26 | 2026-10-26 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel scribe api documentation | Scribe docs
1.3.5 | 3 | Day 15: Tests + buffer | Work package | 3 | 15 | 2026-10-27 | 2026-10-27 | 6.51 | Not started | 0% | 0
1.3.5.1 | 4 | Feature tests: ticket lifecycle, SLA breach, Queue/Notification fakes | Task | 3 | 15 | 2026-10-27 | 2026-10-27 | 2.17 | In progress | 0% | 0 |  | YouTube: laravel queue fake notification fake testing | Laravel docs: Mocking and fakes
1.3.5.2 | 4 | API tests: auth, tenant isolation, rate limit | Task | 3 | 15 | 2026-10-27 | 2026-10-27 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel api testing sanctum | Laravel docs: Sanctum testing
1.3.5.3 | 4 | Catch up on anything unfinished | Task | 3 | 15 | 2026-10-27 | 2026-10-27 | 2.17 | Not started | 0% | 0
1.4 | 2 | Week 4: Python + FastAPI | Phase | 4 |  | 2026-10-28 | 2026-11-03 | 32.54 |  | 0% | 0
1.4.1 | 3 | Day 16: Python fundamentals | Work package | 4 | 16 | 2026-10-28 | 2026-10-28 | 6.51 | Not started | 0% | 0
1.4.1.1 | 4 | Virtual environments and package manager (pip or uv) | Task | 4 | 16 | 2026-10-28 | 2026-10-28 | 2.17 | Not started | 0% | 0 |  | YouTube: python uv package manager tutorial | uv docs
1.4.1.2 | 4 | Types, functions, classes, dataclasses, modules, exceptions, type hints | Task | 4 | 16 | 2026-10-28 | 2026-10-28 | 2.17 | Not started | 0% | 0 |  | YouTube: python for php developers | Python tutorial
1.4.1.3 | 4 | 5 small scripts; compare concepts to PHP in DEVLOG.md | Task | 4 | 16 | 2026-10-28 | 2026-10-28 | 2.17 | Not started | 0% | 0 |  | YouTube: python vs php differences | Search: python vs php concepts compared
1.4.2 | 3 | Day 17: Python for services | Work package | 4 | 17 | 2026-10-29 | 2026-10-29 | 6.5 | Not started | 0% | 0
1.4.2.1 | 4 | Pydantic, async/await basics, HTTP calls with httpx | Task | 4 | 17 | 2026-10-29 | 2026-10-29 | 3.25 | Not started | 0% | 0 |  | YouTube: pydantic async httpx python tutorial | Pydantic docs
1.4.2.2 | 4 | pytest basics: fixtures, parametrize | Task | 4 | 17 | 2026-10-29 | 2026-10-29 | 3.25 | Not started | 0% | 0 |  | YouTube: pytest fixtures parametrize | pytest: Get started
1.4.3 | 3 | Day 18: FastAPI | Work package | 4 | 18 | 2026-10-30 | 2026-10-30 | 6.51 | Not started | 0% | 0
1.4.3.1 | 4 | Routes, request/response models, dependency injection, OpenAPI docs | Task | 4 | 18 | 2026-10-30 | 2026-10-30 | 2.17 | Not started | 0% | 0 |  | YouTube: fastapi tutorial | FastAPI tutorial
1.4.3.2 | 4 | Dockerfile; add service to Docker Compose | Task | 4 | 18 | 2026-10-30 | 2026-10-30 | 2.17 | Not started | 0% | 0 |  | YouTube: fastapi docker compose | FastAPI: Docker
1.4.3.3 | 4 | Laravel calls /health successfully | Task | 4 | 18 | 2026-10-30 | 2026-10-30 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel http client | Laravel docs: HTTP client
1.4.4 | 3 | Day 19: Local AI model | Work package | 4 | 19 | 2026-11-02 | 2026-11-02 | 6.51 | Not started | 0% | 0
1.4.4.1 | 4 | Install Ollama; pull small chat and embedding models | Task | 4 | 19 | 2026-11-02 | 2026-11-02 | 2.17 | Not started | 0% | 0 |  | YouTube: ollama tutorial embedding models | Ollama on GitHub
1.4.4.2 | 4 | Call both from Python; config via env variables | Task | 4 | 19 | 2026-11-02 | 2026-11-02 | 2.17 | Not started | 0% | 0 |  | YouTube: ollama python library | ollama-python on GitHub
1.4.4.3 | 4 | Note model size, RAM use, response time in DEVLOG.md | Task | 4 | 19 | 2026-11-02 | 2026-11-02 | 2.17 | Not started | 0% | 0 |  | YouTube: local llm ram requirements | Search: ollama model size RAM requirements
1.4.5 | 3 | Day 20: Tests + CI + buffer | Work package | 4 | 20 | 2026-11-03 | 2026-11-03 | 6.51 | Not started | 0% | 0
1.4.5.1 | 4 | pytest with TestClient; mock model calls | Task | 4 | 20 | 2026-11-03 | 2026-11-03 | 2.17 | Not started | 0% | 0 |  | YouTube: fastapi testing pytest testclient | FastAPI: Testing
1.4.5.2 | 4 | ruff linting; Python job in GitHub Actions | Task | 4 | 20 | 2026-11-03 | 2026-11-03 | 2.17 | Not started | 0% | 0 |  | YouTube: ruff python linter | Ruff docs
1.4.5.3 | 4 | Catch up on anything unfinished | Task | 4 | 20 | 2026-11-03 | 2026-11-03 | 2.17 | Not started | 0% | 0
1.5 | 2 | Week 5: AI features | Phase | 5 |  | 2026-11-04 | 2026-11-10 | 32.54 |  | 0% | 0
1.5.1 | 3 | Day 21: Embeddings | Work package | 5 | 21 | 2026-11-04 | 2026-11-04 | 6.51 | Not started | 0% | 0
1.5.1.1 | 4 | Learn embeddings and vector similarity | Task | 5 | 21 | 2026-11-04 | 2026-11-04 | 2.17 | Not started | 0% | 0 |  | YouTube: vector embeddings explained | pgvector on GitHub
1.5.1.2 | 4 | KB articles CRUD in Laravel | Task | 5 | 21 | 2026-11-04 | 2026-11-04 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel inertia react crud | Laravel docs: Resource controllers
1.5.1.3 | 4 | Python /embed; Laravel stores vectors in pgvector via queued job | Task | 5 | 21 | 2026-11-04 | 2026-11-04 | 2.17 | Not started | 0% | 0 |  | YouTube: pgvector laravel php | pgvector-php on GitHub
1.5.2 | 3 | Day 22: RAG suggested replies | Work package | 5 | 22 | 2026-11-05 | 2026-11-05 | 6.5 | Not started | 0% | 0
1.5.2.1 | 4 | Laravel pgvector similarity query for top KB chunks | Task | 5 | 22 | 2026-11-05 | 2026-11-05 | 3.25 | Not started | 0% | 0 |  | YouTube: RAG retrieval augmented generation explained | pgvector: Querying
1.5.2.2 | 4 | Python /suggest-reply returns draft with sources used | Task | 5 | 22 | 2026-11-05 | 2026-11-05 | 3.25 | Not started | 0% | 0 |  | YouTube: build RAG fastapi ollama | Search: retrieval augmented generation tutorial
1.5.3 | 3 | Day 23: Auto-triage | Work package | 5 | 23 | 2026-11-06 | 2026-11-06 | 6.51 | Not started | 0% | 0
1.5.3.1 | 4 | Python /triage returns category, priority, confidence as JSON | Task | 5 | 23 | 2026-11-06 | 2026-11-06 | 2.17 | Not started | 0% | 0 |  | YouTube: llm structured output json classification | Search: ollama structured outputs json
1.5.3.2 | 4 | Queued job on TicketCreated stores the suggestion | Task | 5 | 23 | 2026-11-06 | 2026-11-06 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel queue jobs | Laravel docs: Queues
1.5.3.3 | 4 | Low confidence to manual review; agent override | Task | 5 | 23 | 2026-11-06 | 2026-11-06 | 2.17 | Not started | 0% | 0 |  | YouTube: human in the loop AI confidence threshold | Search: human in the loop AI confidence threshold
1.5.4 | 3 | Day 24: Provider layer | Work package | 5 | 24 | 2026-11-09 | 2026-11-09 | 6.51 | Not started | 0% | 0
1.5.4.1 | 4 | One interface, two providers: Ollama and Claude (Claude off) | Task | 5 | 24 | 2026-11-09 | 2026-11-09 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel service container interface binding | Laravel docs: Binding interfaces
1.5.4.2 | 4 | Versioned prompt files; timeouts and retries | Task | 5 | 24 | 2026-11-09 | 2026-11-09 | 2.17 | Not started | 0% | 0 |  | YouTube: prompt versioning llm production | Laravel docs: HTTP retries
1.5.4.3 | 4 | Prompt-injection guard: ticket text treated as data | Task | 5 | 24 | 2026-11-09 | 2026-11-09 | 2.17 | Not started | 0% | 0 |  | YouTube: prompt injection explained | OWASP Top 10 for LLM apps
1.5.5 | 3 | Day 25: UI + tests + buffer | Work package | 5 | 25 | 2026-11-10 | 2026-11-10 | 6.51 | Not started | 0% | 0
1.5.5.1 | 4 | Agent view: show triage + suggested reply; accept/edit/reject | Task | 5 | 25 | 2026-11-10 | 2026-11-10 | 2.17 | Not started | 0% | 0 |  | YouTube: human in the loop AI UX | Inertia docs: Forms
1.5.5.2 | 4 | Laravel tests with Http::fake; pytest per endpoint | Task | 5 | 25 | 2026-11-10 | 2026-11-10 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel http fake testing | Laravel docs: HTTP client testing
1.5.5.3 | 4 | Catch up on anything unfinished | Task | 5 | 25 | 2026-11-10 | 2026-11-10 | 2.17 | Not started | 0% | 0
1.6 | 2 | Week 6: Senior-grade quality | Phase | 6 |  | 2026-11-11 | 2026-11-17 | 32.52 |  | 0% | 0
1.6.1 | 3 | Day 26: AI evaluations | Work package | 6 | 26 | 2026-11-11 | 2026-11-11 | 6.5 | Not started | 0% | 0
1.6.1.1 | 4 | Labeled test set of ~100 tickets (check every label) | Task | 6 | 26 | 2026-11-11 | 2026-11-11 | 3.25 | Not started | 0% | 0 |  | YouTube: llm evals explained | Search: how to build an llm evaluation dataset
1.6.1.2 | 4 | Eval script: accuracy per category + confusion matrix; report in repo | Task | 6 | 26 | 2026-11-11 | 2026-11-11 | 3.25 | Not started | 0% | 0 |  | YouTube: confusion matrix explained | scikit-learn: Confusion matrix
1.6.2 | 3 | Day 27: Improve + measure | Work package | 6 | 27 | 2026-11-12 | 2026-11-12 | 6.5 | Not started | 0% | 0
1.6.2.1 | 4 | Improve prompts; record before/after accuracy | Task | 6 | 27 | 2026-11-12 | 2026-11-12 | 3.25 | Not started | 0% | 0 |  | YouTube: prompt engineering tutorial | Search: prompt engineering guide
1.6.2.2 | 4 | Log tokens and latency per AI call; admin usage page | Task | 6 | 27 | 2026-11-12 | 2026-11-12 | 3.25 | Not started | 0% | 0 |  | YouTube: llm observability tokens latency | Laravel docs: Logging
1.6.3 | 3 | Day 28: Fallbacks | Work package | 6 | 28 | 2026-11-13 | 2026-11-13 | 6.5 | Not started | 0% | 0
1.6.3.1 | 4 | AI down/slow: ticket goes to manual queue | Task | 6 | 28 | 2026-11-13 | 2026-11-13 | 3.25 | Not started | 0% | 0 |  | YouTube: circuit breaker pattern explained | Search: graceful degradation pattern
1.6.3.2 | 4 | Retries with backoff; failed-jobs handling; failure-path tests | Task | 6 | 28 | 2026-11-13 | 2026-11-13 | 3.25 | Not started | 0% | 0 |  | YouTube: laravel failed jobs retry backoff | Laravel docs: Failed jobs
1.6.4 | 3 | Day 29: Observability + security | Work package | 6 | 29 | 2026-11-16 | 2026-11-16 | 6.51 | Not started | 0% | 0
1.6.4.1 | 4 | Structured logs with correlation ID Laravel to Python | Task | 6 | 29 | 2026-11-16 | 2026-11-16 | 2.17 | Not started | 0% | 0 |  | YouTube: correlation id logging microservices | Laravel docs: Context
1.6.4.2 | 4 | Laravel Pulse for app health | Task | 6 | 29 | 2026-11-16 | 2026-11-16 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel pulse | Laravel docs: Pulse
1.6.4.3 | 4 | Security checklist: OWASP, tenant isolation, rate limits, uploads | Task | 6 | 29 | 2026-11-16 | 2026-11-16 | 2.17 | Not started | 0% | 0 |  | YouTube: owasp top 10 explained | OWASP Top 10
1.6.5 | 3 | Day 30: Load test + buffer | Work package | 6 | 30 | 2026-11-17 | 2026-11-17 | 6.51 | Not started | 0% | 0
1.6.5.1 | 4 | k6 load test on ticket creation and API | Task | 6 | 30 | 2026-11-17 | 2026-11-17 | 2.17 | Not started | 0% | 0 |  | YouTube: k6 load testing tutorial | Grafana k6 docs
1.6.5.2 | 4 | Fix one bottleneck; record numbers | Task | 6 | 30 | 2026-11-17 | 2026-11-17 | 2.17 | Not started | 0% | 0 |  | YouTube: postgres explain analyze | PostgreSQL: Using EXPLAIN
1.6.5.3 | 4 | Catch up on anything unfinished | Task | 6 | 30 | 2026-11-17 | 2026-11-17 | 2.17 | Not started | 0% | 0
1.7 | 2 | Week 7: Deploy + showcase | Phase | 7 |  | 2026-11-18 | 2026-11-24 | 32.54 |  | 0% | 0
1.7.1 | 3 | Day 31: AWS setup | Work package | 7 | 31 | 2026-11-18 | 2026-11-18 | 6.51 | Not started | 0% | 0
1.7.1.1 | 4 | AWS account on Free plan; billing alert first | Task | 7 | 31 | 2026-11-18 | 2026-11-18 | 2.17 | Not started | 0% | 0 |  | YouTube: aws billing alert budget setup | AWS Free Tier
1.7.1.2 | 4 | IAM user, EC2 instance, security groups, SSH key | Task | 7 | 31 | 2026-11-18 | 2026-11-18 | 2.17 | Not started | 0% | 0 |  | YouTube: aws ec2 tutorial security groups ssh | AWS EC2 docs
1.7.1.3 | 4 | Install Docker on the instance | Task | 7 | 31 | 2026-11-18 | 2026-11-18 | 2.17 | Not started | 0% | 0 |  | YouTube: install docker on ec2 | Docker: Install on Ubuntu
1.7.2 | 3 | Day 32: Production stack | Work package | 7 | 32 | 2026-11-19 | 2026-11-19 | 6.51 | Not started | 0% | 0
1.7.2.1 | 4 | Production Compose: Nginx, PHP-FPM, Horizon, scheduler, PostgreSQL, Redis, Python | Task | 7 | 32 | 2026-11-19 | 2026-11-19 | 2.17 | Not started | 0% | 0 |  | YouTube: laravel docker production deployment | Laravel docs: Deployment
1.7.2.2 | 4 | Secrets in env files, never in Git | Task | 7 | 32 | 2026-11-19 | 2026-11-19 | 2.17 | Not started | 0% | 0 |  | YouTube: secrets management env files | Laravel docs: Environment config
1.7.2.3 | 4 | sslip.io hostname + Let's Encrypt HTTPS | Task | 7 | 32 | 2026-11-19 | 2026-11-19 | 2.17 | Not started | 0% | 0 |  | YouTube: lets encrypt nginx certbot docker | sslip.io
1.7.3 | 3 | Day 33: CD + Claude decision | Work package | 7 | 33 | 2026-11-20 | 2026-11-20 | 6.5 | Not started | 0% | 0
1.7.3.1 | 4 | GitHub Actions deploy over SSH after tests pass; smoke test | Task | 7 | 33 | 2026-11-20 | 2026-11-20 | 3.25 | Not started | 0% | 0 |  | YouTube: github actions deploy ssh docker | GitHub Actions docs
1.7.3.2 | 4 | Decide on Claude API; if yes, run evals on Haiku 4.5 vs local model | Task | 7 | 33 | 2026-11-20 | 2026-11-20 | 3.25 | Not started | 0% | 0 |  | YouTube: claude api tutorial | Anthropic docs
1.7.4 | 3 | Day 34: Documentation | Work package | 7 | 34 | 2026-11-23 | 2026-11-23 | 6.51 | Not started | 0% | 0
1.7.4.1 | 4 | README: architecture diagram, setup, screenshots, test/eval results | Task | 7 | 34 | 2026-11-23 | 2026-11-23 | 2.17 | Not started | 0% | 0 |  | YouTube: c4 model architecture diagrams | C4 model
1.7.4.2 | 4 | Finalize ADRs; clean repo; record screen walkthrough | Task | 7 | 34 | 2026-11-23 | 2026-11-23 | 2.17 | Not started | 0% | 0 |  | YouTube: architecture decision records | ADR GitHub organization
1.7.4.3 | 4 | Stop EC2 instance to save credits | Task | 7 | 34 | 2026-11-23 | 2026-11-23 | 2.17 | Not started | 0% | 0 |  | YouTube: aws ec2 stop instance save cost | AWS EC2 docs
1.7.5 | 3 | Day 35: CV + interview prep | Work package | 7 | 35 | 2026-11-24 | 2026-11-24 | 6.51 | Not started | 0% | 0
1.7.5.1 | 4 | Add project to CV with real numbers | Task | 7 | 35 | 2026-11-24 | 2026-11-24 | 2.17 | Not started | 0% | 0 |  | YouTube: how to describe projects on resume software engineer | Search: software engineer resume project quantified impact
1.7.5.2 | 4 | Write and answer aloud 10 interview questions | Task | 7 | 35 | 2026-11-24 | 2026-11-24 | 2.17 | Not started | 0% | 0 |  | YouTube: system design interview multi tenant saas | Search: laravel senior developer interview questions
1.7.5.3 | 4 | Optional: LinkedIn post | Task | 7 | 35 | 2026-11-24 | 2026-11-24 | 2.17 | Not started | 0% | 0 |  | YouTube: linkedin post developer portfolio project | Search: linkedin post developer portfolio project
Formulas:
Start = [Start, row below]
Start = WORKDAY(C2,[Day]-1)
Finish = [Finish, row below]
Finish = [Start]

## Summary
Progress by week
Week | Phase | Start | Finish | Est. hours | Earned hours | % complete | Tasks done | Tasks total
1 | Week 1: Foundations | 2026-10-07 | 2026-10-07 | 32.49 | 32.49 | 100% | 17 | 17
2 | Week 2: Frontend | 2026-10-14 | 2026-10-20 | 32.53 | 3.25 | 9.991% | 1 | 13
3 | Week 3: Business logic | 2026-10-21 | 2026-10-27 | 32.54 | 0 | 0% | 0 | 14
4 | Week 4: Python + FastAPI | 2026-10-28 | 2026-11-03 | 32.54 | 0 | 0% | 0 | 14
5 | Week 5: AI features | 2026-11-04 | 2026-11-10 | 32.54 | 0 | 0% | 0 | 14
6 | Week 6: Senior-grade quality | 2026-11-11 | 2026-11-17 | 32.52 | 0 | 0% | 0 | 12
7 | Week 7: Deploy + showcase | 2026-11-18 | 2026-11-24 | 32.54 | 0 | 0% | 0 | 14
| Total | 2026-10-07 | 2026-11-24 | 227.7 | 35.74 | 15.7% | 18 | 98
% complete counts In progress tasks as 50%. Status 'Cut' tasks count as not earned.
Formulas:
Finish = [Finish, row above]